## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [5 empty] | Week #3 (10 hrs / week) | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12
|  |  |  | 2014-07-16 | 2014-07-17 | 2014-07-18 | 2014-07-19 | 2014-07-20 | 2014-07-21 | 2014-07-22 | 2014-07-23 | 2014-07-24 | 2014-07-25 | 2014-07-26 | 2014-07-27
|  |  | 160 | 160 | 151 | 142 | 133 | 124 | 115 | 106 | 97 | 88 | 79 | 70 | 61 | Ideal Burndown
|  |  | 121 | 117 | 113 | 111 | 106 | 103 | 95 | 85 | 63 | 45 | 30 | 15 |  | Remaining Hrs (Total)
| Set up Gradle project to implement API's for starbucks project | Sourabh+Pratik | 2 | bar: 2014-07-16 to 2014-07-27
Initial work | Setting up MySQL Workbench as a database for project | Sourabh+Pratik | 2 | bar: 2014-07-16 to 2014-07-27
Spike | project overview | Sourabh+Pratik+Hrishikesh+Tarun | 14 | 2014-07-16: 2; 2014-07-17: 2; 2014-07-18: 2; 2014-07-19: 2; 2014-07-20: 2
Rest API implementation | Implement Customer API | Pratik | 14 | 2014-07-22: 2; 2014-07-23: 4; 2014-07-24: 4; 2014-07-25: 2
| Database Design | Sourabh+Pratik+Hrishikesh+Tarun | 5 | bar: 2014-07-16 to 2014-07-27
| Implement Order API | Sourabh | 14 | 2014-07-19: 2; 2014-07-21: 2; 2014-07-23: 4; 2014-07-24: 2; 2014-07-25: 2
| Implement Menu API | Tarun | 14 | 2014-07-21: 4; 2014-07-23: 4; 2014-07-25: 2; 2014-07-26: 4
| Implement Card API | Hrishikesh | 14 | 2014-07-22: 4; 2014-07-23: 4; 2014-07-24: 6
| Test Customer API | Pratik | 6 | 2014-07-22: 2; 2014-07-23: 2; 2014-07-26: 2
| Test order API | Sourabh | 6 | 2014-07-23: 2; 2014-07-24: 2; 2014-07-25: 2
| Test Menu API | Tarun | 6 | 2014-07-24: 2; 2014-07-25: 2; 2014-07-26: 2
| Test Card API | Hrishikesh | 6 | 2014-07-23: 2; 2014-07-24: 2; 2014-07-26: 2
Deploy the application in Docker | Deploy the application in container | Sourabh+Pratik | 5 | 2014-07-25: 2; 2014-07-26: 1
Deploy on cloud | Deploy the application on cloud | Sourabh+Pratik | 5 | 2014-07-25: 2; 2014-07-26: 1
Code Review |  | Hrishikesh+Tarun | 8 | 2014-07-21: 2; 2014-07-22: 2; 2014-07-25: 1; 2014-07-26: 3
Team:
Sourabh Namilikonda | 20 hours / Week
Pratik Dhumal | 20 hours / Week
Hrishikesh Rendalkar | 20 hours / Week
Tarun Shetty | 20 hours / Week
Total Available Hours During Sprint: | 160